## HOME
JAIHOBAY.COM
VERSION BY:2207 |  |  |  | VERIFIED BY:RUGMA MA'AM
TESTED BY:C.ARDHRA.HARI |  |  |  | DATE:12-05-2024
TESTID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
HOME
JHB_RP_01 | Check whether the home screen appears when the application is opened | Open the app | N/A | Home screen should appear when the application is opened | Home screen appeared after application opened | PASS
JHB_RP_02 | Check whether the Home screen has launched without any interuption | Open the app | N/A | Home screen should launch without any interuption | Home screen is launched without any interuption | PASS
JHB_RP_03 | Check whether the Home screen is shown clearly | Open the app | N/A | Should show Home screen clearly | Home screen is shown clearly | PASS
JHB_RP_04 | Check whether proper logo given | Open the app | N/A | The logo should be proper | There is no proper logo given | FAIL
JHB_RP_05 | Check whether the logo is clearly visible for the user | Open the app | N/A | The logo should be clearly visible for the user | The logo is clearly visible for the user | PASS
JHB_RP_06 | Check the size of the logo is correct | Open the app | N/A | The logo size should be correct | The logo size is small | FAIL
JHB_RP_07 | Check the color of the Home screen | Open the app | N/A | Should be eye catching | It is eye catching | PASS
JHB_RP_08 | Check whether address in home when clicked it redirects to correct address | Open the app | N/A | Address in homepage when clicked should redirect to correct page | Address in homepage when clicked error page is appeared | FAIL
JHB_RP_09 | Check whether logo is present in footer section | Open the app | N/A | Logo should be present in the footer section | Logo is not present in the footer section | FAIL

## HOMEPAGE
HOMEPAGE
TESTID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
JHB_RP_01 | Check whether Zooming is possible | Open the site | N/A | Zooming should be possible | Zooming is possible | PASS
JHB_RP_02 | Check whether address mentioned on top of the page redirects to correct page | Open the site | N/A | Address on top of page should redirect to correct page | Address on top when clicked is showing error page | FAIL
JHB_RP_03 | Check whether the contact number mentioned on top of the page is redirecting | Open the site | N/A | Contact option should redirect to correct page | Contact option is not redirecting to correct page | FAIL
JHB_RP_04 | Check whether the Emaiild on top of page is redirecting to correct page | Open the site | N/A | Emailid should redirect to correct page | Emailid is not redirecting to correct page | FAIL
JHB_RP_05 | Check whether my account option in homepage when clicked is redirected | Open the site | N/A | my account option should redirect to correct page when clicked | my account option is not redirecting to correct page when clicked | FAIL
JHB_RP_06 | Check whether login option in homepage when clicked is redirected to new page | Open the site | N/A | login option should redirect to correct page when clicked | login option is not redirecting to correct page when clicked | FAIL
JHB_RP_07 | Check whether in search option any product when searched the details are shown or not | Open the site | N/A | The details of any product should be shown when searched in search option | The details of any product is not shown when searched in search option | FAIL
JHB_RP_08 | Check whether wish list shows title | Open the site | N/A | The wishlist should show title | The wishlist is only showing details not titlte | FAIL
JHB_RP_09 | Check whether in cart it shows the details we added | Open the site | N/A | The cart should show details we add | The cart shows the details of product we had added | PASS
JHB_RP_10 | Check whether the search option in image is working | Open the site | N/A | The search option in image should work | The search option in image is not working | FAIL
JHB_RP_11 | Check whether Currency change option is given | Open the site | N/A | Currency change option should be available | Currency change option is not available | FAIL
JHB_RP_12 | Check whether all transaction mode given is redirecting to correct page | Open the site | N/A | All transaction mode should redirect to correct page | All transaction mode is redirecting to correct page | PASS
JHB_RP_13 | Check whether the address in footer section is correct | Open the site | N/A | Address in footer section should be correct | Address in footer section is when clicked error page is opened | FAIL
JHB_RP_14 | Check whether the contact number in footer section is correct | Open the site | N/A | Contact number should be correct | Contact number is not redirecting to correct page | FAIL
JHB_RP_15 | Check whether the Emailid in footer section is correct | Open the site | N/A | Emailild should be correct | Emailid is not redirecting to correct page | FAIL
JHB_RP_16 | Check whether the download app option is redirecting to correct page | Open the site | N/A | Download app option should redirect to correct page | Download app option is redirected to correct page | PASS
JHB_RP_17 | Check whether social media in footer section is redirecting to correct page | Open the site | N/A | Social media in footer section should redirect to correct page | Social media is not redirected to correct page | FAIL
JHB_RP_18 | Check whether the social media in footer section retaining after two tabs | Open the site | N/A | Social media in footer section should retain after two tabs | Social media is not retained after two tabs | FAIL
JHB_RP_19 | Check whether new arrivals are mentioned on top of page | Open the site | N/A | New arrivals should be mentioned on top of page | New arrivals are mentioned below of page | FAIL
JHB_RP_20 | Check whether top rated products are mentioned on top of the page | Open the site | N/A | Top rated products should be mentioned on top of page | Top rated products are mentioned below of page | FAIL
JHB_RP_21 | Check whether any product image when clicked shows product details | Open the site | N/A | Any product image when clicked should show product details | Any product image when clicked is showing product details | PASS
JHB_RP_22 | Check whether limit of product that can be added to cart | Open the site | N/A | product limit should be there | product limit is not there | FAIL

## ALLPRODUCTS
ALLPRODUCTS
TESTID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
JHB_RP_01 | Check the alignment of the fields | verify fields arranged properly | N/A | Should be properly aligned | Fields are properly aligned | PASS
JHB_RP_02 | Check if any field is overlapping with eachother | verify fields overlapping | N/A | Should not overlap with eachother | Fields are not overlapping with eachother | PASS
JHB_RP_03 | Check zooming of options is possible | 1.open the site 2.Double click on it | N/A | Zooming of options should be possible | Zooming of options is possible | PASS
JHB_RP_04 | Check whether women option showing only women products | Open the site | N/A | Women option should show only women item | Women option is also showing baby items list other than women products | FAIL
JHB_RP_05 | Check whether women product images can be zoomed | Open the site | N/A | Women product option images should be zoomed | Women product image can be zoomed | PASS
JHB_RP_06 | Check whether images of product are overlapping | Open the site | N/A | Product images should not overlap | Product images are not overlapped | PASS
JHB_RP_07 | Check whether men option showing only men products | Open the site | N/A | Men option should show only men item | Men option is showing only men products list | PASS
JHB_RP_08 | Check whether men option images can be zoomed | Open the site | N/A | Men product option images should be zoomed | Men product image can be zoomed | PASS
JHB_RP_09 | Check whether images of men product are overlapping | Open the site | N/A | Men Product images should not overlap | Men product images are not overlapping | PASS
JHB_RP_10 | Check whether accessories images can be zoomed | Open the site | N/A | Accessories images should be zoomed | Accessories images can be zoomed | PASS
JHB_RP_11 | Check whether accessories images are overlapping | Open the site | N/A | Accessories images should not overlap | Accessories images are not overlapped | PASS
JHB_RP_12 | Check whether accessories list when clicked showing many products | Open the site | N/A | Accessories list should show many products | Accessories list when clicked showing only limited products list | FAIL
JHB_RP_13 | Check whether contact field in section option given is correct | Open the site | N/A | Contact option should be correct when clicked | Contact option when clicked page showing Non-existent changeset UUID | FAIL
JHB_RP_14 | Check whether blog option in section option given shows details | Open the site | N/A | Blog option should show details | Blog option when clicked page showing Non-existent changeset UUID | FAIL
JHB_RP_15 | Check whether cart option in section option shows details of product added | Open the site | N/A | Cart option should show details of product added | Cart option details of product added are shown | PASS
JHB_RP_16 | Check whether shop option in section option shows all product details | Open the site | N/A | Shop option should show all product details | Shop option is showing all product details | PASS
JHB_RP_17 | Check whether in shop option images of product are overlapping | Open the site | N/A | Images of product in shop option should not overlap | Images of product in shop option is not overlapping | PASS
JHB_RP_18 | Check whether in blog option given shows blog details | Open the site | N/A | Blog option should show details | Blog option is not showing blog details | FAIL
JHB_RP_19 | Check whether baby products are showing only baby products | Open the site | N/A | Baby products should show only baby products | Baby products is showing only baby products | PASS
JHB_RP_20 | Check whether baby products images are overlapping | Open the site | N/A | Baby products images should not overlap | Baby products images are not overlapping | PASS
JHB_RP_21 | Check whether Gym equipments option shows only gym products | Open the site | N/A | Gym equipments should show only gym products | Gym equipments option is showing only gym products | PASS
JHB_RP_22 | Check whether Furniture and Dining Table option is opened when clicked | Open the site | N/A | Furniture and Dining Table option should be opened when clicked | Furniture and Dining Table option is not opened when clicked | FAIL
JHB_RP_23 | Check whether Essentials option show most essential product | Open the site | N/A | Essentials option should show most essential product | Essentials option shows the most essential product | PASS
JHB_RP_24 | Check whether Lights and Decorations option shows only light and decoration | Open the site | N/A | Lights and Decoration option should show only light and decoration | Lights and Decoration option is showing light and decoration | PASS
JHB_RP_25 | Check whether Peacock Wall Clock option is showing only correct product | Open the site | N/A | Peacock Wall Clock option should show only correct product | Peacock Wall Clock option is showing only correct product | PASS
JHB_RP_26 | Check whether bicycle option shows only bicycle images | Open the site | N/A | Bicycle option should show only Bicycle images | Bicycle option is showing only Bicycle images | PASS
JHB_RP_27 | Check whether toys option is showing only toys | Open the site | N/A | Toys option should show only toys | Toys option is showing only toys | PASS
JHB_RP_28 | Check whether Deals of the Day shows the product image with details | Open the site | N/A | Deals of the Day should show product image with details | Deals of the Day is showing product image with details | PASS
JHB_RP_29 | Check whether Health and Nutrition option shows the correct page | Open the site | N/A | Health and Nutrition option should show the correct page | Health and Nutrition option page is showing page not found | FAIL
JHB_RP_30 | Check whether Party items option show only party items | Open the site | N/A | Party items option should show only party items | Party items option is showing only party items | PASS
JHB_RP_31 | Check whether Beds option display only beds | Open the site | N/A | Beds option should display only beds | Beds option displays many products not beds | FAIL
JHB_RP_32 | Check whether Electronics option shows many electronic products | Open the site | N/A | Electronics option should show many electronic products | Electronic option shows only limited products | FAIL
JHB_RP_33 | Check whether in cart,recent comments,archives,categories, popular posts is opened when clicked | Open the site | N/A | All the options in cart should open when clicked | All the options in cart is not opening when clicked | FAIL
JHB_RP_34 | Check whether when adding quantity the amount changes automatically | Open the site | N/A | When Adding quantity the amount should change automatically | When Adding quantity the amount is not changing automatically | FAIL
JHB_RP_35 | Check whether deleting an item from cart is reflecting cart symbol | Open the site | N/A | Deleting an item from cart should reflect cart symbol | Deleting an item from cart does not reflect cart symbol | FAIL
JHB_RP_36 | Check whether name field in your review option is accepting only characters | Input characters in name field | Characters | Name field should only read characters | Name field is accepting numbers other than characters | FAIL
JHB_RP_37 | Check whether Emailid in your review option is accepting characters, numbers | Input Characters and numbers | Characters and Numbers | Emailid should accept characters and numbers | Emailid is accepting characters and numbers | PASS
JHB_RP_38 | Check whether Menu is hidden from AllProduct | Open the site | N/A | Menu should be hidden from AllProducts | Menu is not hidden from All Products | FAIL

## BUG REPORT
JAIHOBAY.COM
IDENTIFIED BY:C.ARDHRA.HARI
REPORTED TO:RUGMA MA'AM
DATE:12-05-2024
ENVIRONMENTAL DETAILS:WINDOWS 10
BUGID | TESTID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | SCREENSHOT | STATUS
BR_JHB_RP_01 | JHB_RP_01 | The logo should be proper | There is no proper logo given | 1.open the html file 2.Add logo image 3.Add Styling with CSS 4.Save the file and test it | Major | Medium |  | New
BR_JHB_RP_02 | JHB_RP_02 | The logo size should be correct | The logo size is small | 1.open the html file 2.Add logo image 3.Adjust size 4.Add Styling with CSS 5.Save the file and test it | Major | Medium |  | New
BR_JHB_RP_03 | JHB_RP_03 | Address in homepage when clicked should redirect to correct page | Address in homepage when clicked error page is appeared | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_04 | JHB_RP_04 | Logo should be present in the footer section | Logo is not present in the footer section | 1.open the html file 2.Edit the code 3.Add logo image | Minor | Medium |  | New
BR_JHB_RP_05 | JHB_RP_05 | Address on top of page should redirect to correct page | Address on top when clicked is showing error page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_06 | JHB_RP_06 | Contact option should redirect to correct page | Contact option is not redirecting to correct page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_07 | JHB_RP_07 | Emailid should redirect to correct page | Emailid is not redirecting to correct page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_08 | JHB_RP_08 | myaccount option should redirect to correct page | myaccount option is not redirecting to correct page when clicked | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_09 | JHB_RP_09 | login option should redirect to correct page when clicked | login option is not redirecting to correct page when clicked | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_10 | JHB_RP_10 | The details of any product should be shown when searched in search option | The details of any product is not shown when searched in search option | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_11 | JHB_RP_11 | The wishlist should show title | The wishlist is only showing details not title | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_12 | JHB_RP_12 | The search option in image should work | The search option in image is not working | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_13 | JHB_RP_13 | Currency change option should be available | Currency change option is not available | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_14 | JHB_RP_14 | Address in footer section should be correct | Address in footer section when clicked error page is opened | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_15 | JHB_RP_15 | Contact in footer section should be correct | Contact number is not redirecting to correct page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_16 | JHB_RP_16 | Emailid in footer section should be correct | Emailid is not redirecting to correct page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_17 | JHB_RP_17 | Social media in footer section should redirect to correct page | Social media is not redirected correct page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_18 | JHB_RP_18 | Social media in footer section should retain after two tabs | Social media is not retained after two tabs | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_19 | JHB_RP_19 | New Arrivals should be mentioned on top of page | New Arrivals are mentioned below the page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_20 | JHB_RP_20 | Top rated product should be mentioned on top of page | Top rated product are mentioned below the page | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_21 | JHB_RP_21 | Product limit should be there for cart | Product limit is not there for cart | 1.open the html file 2.Edit the code | Major | Medium |  | New
BR_JHB_RP_22 | JHB_RP_22 | Women option should show only women items | Women option is also showing baby items list other than women products | 1.open the html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_23 | JHB_RP_23 | Accessories list should show many products | Accessories list when clicked showing only limited products list | 1.open the html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_24 | JHB_RP_24 | Contact option should be correct when clicked | Contact option when clicked page showing Non- existent changeset UUID | 1.open the html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_25 | JHB_RP_25 | Blog option should show details | Blog option when clicked page showing Non- existent changeset UUID | 1.open the html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_26 | JHB_RP_26 | Blog option should show details | Blog option is showing blog details | 1.open the html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_27 | JHB_RP_27 | Furniture and Dining Table option should be opened when clicked | Furniture and Dining Table option is not opened when clicked | 1.open the html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_28 | JHB_RP_28 | Health and Nutrition option should show the correct page | Health and Nutrition option page is showing page not found | 1.open the site 2.Check internet connection | Major | Medium |  | New
BR_JHB_RP_29 | JHB_RP_29 | Beds option should display only beds | Beds option displays many products not beds | 1.open html file 2.Edit the html code | Major | Medium |  | New
BR_JHB_RP_30 | JHB_RP_30 | Electronics option should show many electronic products | Electronic option shows only limited products | 1.open html file 2.Add more electronic products | Major | Medium |  | New
BR_JHB_RP_31 | JHB_RP_31 | All the options in cart should open when clicked | All the options in cart is not opening when clicked | open the site | Critical | High |  | New
BR_JHB_RP_32 | JHB_RP_32 | When adding quantity the amount should change automatically | When adding quantity the amount is not changing automatically | open the site | Major | High |  | New
BR_JHB_RP_33 | JHB_RP_33 | Deleting an item from cart should reflect cart symbol | Deleting an item from cart does not reflect cart symbol | open the site | Major | Medium |  | New
BR_JHB_RP_34 | JHB_RP_34 | Name field should only read characters | Name field is accepting numbers other than characters | 1.open registration page 2.Make changes in html code | Major | Medium |  | New
BR_JHB_RP_35 | JHB_RP_35 | Menu should be hidden from AllProducts | Menu is not hidden from All Products | 1.open html file 2.Edit html code | Major | Medium |  | New

## DEFECT DISTRIBUTION
DEFECT DISTRIBUTION
MODULE NAME | DEFECT DISTRIBUTION
HOME | 4
HOMEPAGE | 17
ALLPRODUCTS | 14

## TEST REPORT
TEST REPORT
MODULE NAME | TEST PASS | TEST FAIL | TOTAL TEST CASES
HOME | 5 | 4 | 9
HOMEPAGE | 5 | 17 | 22
ALLPRODUCTS | 24 | 14 | 38